## Pre-Production Summary
Project Name
Total Estimated Assets & Implementation Times | (See other sheets for breakdowns)
Total Model Time: | 957
Total Rigging and Animation Time: | 5.8
Total Scripting Time: | 25.1
Total VFX Time: | 22.4
Total SFX Time: | 26.6
Total UI Time: | 21.7
Total Time: | 1058.6
Scale
Unit Size:
Notes:
Unknowns

## Models
Models | Category | Model Time | UV Map Time | Texture Time | LightingTime | Approval/Adjustment Time | Total Time For Model
Low-Res Models
low rez camera lens | large | 3 |  | 0 | 0 | 0 | 3
low rez flash | medium | 3 |  | 0 | 0 | 0 | 3
low rez knob | medium | 3 |  | 0 | 0 | 0 | 3
low rez cluster | medium | 3 |  | 0 | 0 | 0 | 3
low rez camera body | large | 3 |  |  |  | 0 | 0
Note: all times are measured in minutes | [5 empty] | Total Low-Res Model Time: | 12
Medium-Res Models
camera main body | large | 15 |  |  |  |  | 15
back black plate | large | 70 |  |  |  |  | 70
front black plate | large | 60 |  |  |  |  | 60
camera lens | large | 40 |  |  |  |  | 40
body lens connection | large | 25 |  |  |  |  | 25
connector side piece | small | 15 |  |  |  |  | 15
camera lens glass | medium | 15 |  |  |  |  | 15
pin on lens | small | 5 |  |  |  |  | 5
pin holder on lens | small | 20 |  |  |  |  | 20
cube on lens top | small | 15 |  |  |  |  | 15
cube on lens bottom | small | 7 |  |  |  |  | 7
front button | small | 7 |  |  |  |  | 7
patch 1 | small | 25 |  |  |  |  | 25
patch 2 | small | 17 |  |  |  |  | 17
top piece main body | meduim | 20 |  |  |  |  | 20
Front plate | medium | 15 |  |  |  |  | 15
snug support | small | 10 |  |  |  |  | 10
top block | small | 7 |  |  |  |  | 7
middle plate | small | 6 |  |  |  |  | 6
eye hole | small | 16 |  |  |  |  | 16
top to back connector | small | 15 |  |  |  |  | 15
highest piece | small | 17 |  |  |  |  | 17
eye hole glass | small | 12 |  |  |  |  | 12
side hole 1 | small | 15 |  |  |  |  | 15
side hole 2 | small | 12 |  |  |  |  | 12
plug in hole M | small | 13 |  |  |  |  | 13
plug in hole X | small | 5 |  |  |  |  | 5
side block | medium | 5 |  |  |  |  | 5
side hinge | medium | 14 |  |  |  |  | 14
side patch | small | 10 |  |  |  |  | 10
front lever knob | small | 13 |  |  |  |  | 13
small simple button | small | 8 |  |  |  |  | 8
large knob w/lever | medium | 12 |  |  |  |  | 12
layer knob | small | 7 |  |  |  |  | 7
glass dome | small | 7 |  |  |  |  | 7
simple switch | small | 3 |  |  |  |  | 3
complex knob rectangle | small | 8 |  |  |  |  | 8
complex knob slant cube | small | 7 |  |  |  |  | 7
complex knob mini knob | small | 13 |  |  |  |  | 13
complex knob body | small | 15 |  |  |  |  | 15
bottom hole | small | 11 |  |  |  |  | 11
large bottom knob | medium | 22 |  |  |  |  | 22
Note: all times are measured in minutes | [5 empty] | Total Medium-Res Model Time: | 654
High-Res Models
camera main body | large | 0 | 6 |  |  |  | 6
back black plate | large | 7 | 7 |  |  |  | 14
front black plate | large | 7 | 8 |  |  |  | 15
camera lens | large | 0 | 7 |  |  |  | 7
body lens connection | large | 0 | 4 |  |  |  | 4
connector side piece | small | 0 | 2 |  |  |  | 2
camera lens glass | medium | 0 | 2 |  |  |  | 2
pin on lens | small | 3 | 3 |  |  |  | 6
pin holder on lens | small | 0 | 5 |  |  |  | 5
cube on lens top | small | 5 | 5 |  |  |  | 10
cube on lens bottom | small | 6 | 4 |  |  |  | 10
front button | small | 0 | 5 |  |  |  | 5
patch 1 | small | 0 | 1 |  |  |  | 1
patch 2 | small | 0 | 1 |  |  |  | 1
top piece main body | meduim | 20 | 8 |  |  |  | 28
Front plate | medium | 8 | 6 |  |  |  | 14
snug support | small | 1 | 2 |  |  |  | 3
top block | small | 0 | 2 |  |  |  | 2
middle plate | small | 0 | 2 |  |  |  | 2
eye hole | small | 0 | 5 |  |  |  | 5
top to back connector | small | 0 | 6 |  |  |  | 6
highest piece | small | 6 | 7 |  |  |  | 13
eye hole glass | small | 0 | 2 |  |  |  | 2
side hole 1 | small | 6 | 6 |  |  |  | 12
side hole 2 | small | 5 | 5 |  |  |  | 10
plug in hole M | small | 0 | 8 |  |  |  | 8
plug in hole X | small | 0 | 7 |  |  |  | 7
side block | medium | 5 | 3 |  |  |  | 8
side hinge | medium | 0 | 5 |  |  |  | 5
side patch | small | 0 | 2 |  |  |  | 2
front lever knob | small | 6 | 5 |  |  |  | 11
small simple button | small | 0 | 4 |  |  |  | 4
large knob w/lever | medium | 3 | 7 |  |  |  | 10
layer knob | small | 0 | 6 |  |  |  | 6
glass dome | small | 0 | 4 |  |  |  | 4
simple switch | small | 0 | 1 |  |  |  | 1
complex knob rectangle | small | 0 | 4 |  |  |  | 4
complex knob slant cube | small | 0 | 6 |  |  |  | 6
complex knob mini knob | small | 0 | 6 |  |  |  | 6
complex knob body | small | 3 | 9 |  |  |  | 12
bottom hole | small | 1 | 5 |  |  |  | 6
large bottom knob | medium | 0 | 6 |  |  |  | 6
[6 empty] | Total High-Res Model Time: | 291
Note: all times are measured in minutes | [5 empty] | Total Model Time: | 957

## Rigging and Animation
Model To Animate | Category | Rig Time | Animation Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Animation
Characters
BabaYagaHut | Large | 3 | 1 | 0.5 | 0.3 | 1 | 5.8
[6 empty] | Total Character Animation Time: | 5.8
[6 empty] | Total Rig & Animation Time: | 5.8

## Scripts
Scripts | Category | Coding Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Script
Player
PlayerMovement | Medium | 2 | 0.5 | 0.5 | 1 | 4
CameraControl | Small | 1 | 0.3 | 0.2 | 1 | 2.5
Jump | Small | 1 | 0.3 | 0.2 | 2 | 3.5
[5 empty] | Total Player Script Time: | 10
Game Events
GameReset | Small | 1 | 0.3 | 0.2 | 0.5 | 2
PlayerDeath | Small | 1 | 0.2 | 0.1 | 0.5 | 1.8
CollectItem | Medium | 2 | 0.5 | 0.5 | 1 | 4
[5 empty] | Total Events Script Time: | 7.8
Rendering
CullingObjects | Small | 1 | 0.2 | 0.2 | 1 | 2.4
TexReplacer(?) | Medium | 2 | 0.4 | 0.5 | 2 | 4.9
[5 empty] | Total Rendering Script Time: | 7.3
[5 empty] | Total Script Time: | 25.1

## VFX
VFX | Category | Art/Script Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For VFX
Camera
Shake | Medium | 0.3 | 1.5 | 0.3 | 1 | 3.1
Collect | Small | 0.3 | 1 | 0.2 | 1 | 2.5
Death | Medium | 0.3 | 1 | 0.3 | 1 | 2.6
[5 empty] | Total Camera VFX Time: | 8.2
Environmental
Fog | Large | 2 | 2 | 0.4 | 1 | 5.4
[5 empty] | Total Environmental VFX Time: | 5.4
Event
WoodCrack | Small | 1 | 1 | 0.5 | 0.5 | 3
DustPoof | Small | 1 | 1 | 0.5 | 0.5 | 3
CollectSparkle | Small | 1 | 1 | 0.3 | 0.5 | 2.8
[5 empty] | Total Event VFX Time: | 8.8
[5 empty] | Total VFX Time: | 22.4

## SFX
SFX | Category | Recording/Editing Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For SFX
Player
Damage | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Jump | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Landing | Small | 0.3 | 1 | 0.2 | 0.5 | 2
HeavyLanding | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Death | Medium | 1 | 1 | 0.2 | 1 | 3.2
[5 empty] | Total Player SFX Time: | 11.2
Environmental
BackgroundCreaks | Large | 2 | 1 | 0.5 | 1 | 4.5
BabaYagaHutStomp | Medium | 0.5 | 2 | 0.5 | 1 | 4
[5 empty] | Total Environmental SFX Time: | 8.5
Event
WoodCrack | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
DustPoof | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
CollectSparkle | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
[5 empty] | Total Event SFX Time: | 6.9
[5 empty] | Total SFX Time: | 26.6

## UI
UI | Category | Art/Scripting Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For UI
Camera
CrackScreen | Medium | 2 | 2 | 0.2 | 0.5 | 4.7
Collectable | Small | 1 | 1 | 0.2 | 0.5 | 2.7
FadeScreen | Small | 0.3 | 2 | 0.2 | 1 | 3.5
[5 empty] | Total Camera UI Time: | 10.9
Front End
TitleScreen | Large | 2 | 1 | 0.5 | 1 | 4.5
[5 empty] | Total Front End UI Time: | 4.5
Pause
PauseMenu | Large | 3 | 2 | 0.3 | 1 | 6.3
[5 empty] | Total Pause UI Time: | 6.3
[5 empty] | Total UI Time: | 21.7