## Pre-Production Summary
Project Name
Total Estimated Assets & Implementation Times | (See other sheets for breakdowns)
Total Model Time: | 655
Total Rigging and Animation Time: | 5.8
Total Scripting Time: | 25.1
Total VFX Time: | 22.4
Total SFX Time: | 26.6
Total UI Time: | 21.7
Total Time: | 756.6
Scale
Unit Size:
Notes:
Unknowns

## Models
Models | Category | Model Time | UV Map Time | Texture Time | LightingTime | Approval/Adjustment Time | Total Time For Model
Low-Res Models
low rez camera lens | large | 3 |  | 0 | 0 | 0 | 3
low rez flash | medium | 3 |  | 0 | 0 | 0 | 3
low rez knob | medium | 3 |  | 0 | 0 | 0 | 3
low rez cluster | medium | 3 |  | 0 | 0 | 0 | 3
low rez camera body | large | 3 |  |  |  | 0 | 0
Note: all times are measured in minutes | [5 empty] | Total Low-Res Model Time: | 12
Medium-Res Models
camera lens | large | 30 |  |  |  |  | 30
small simple button | small | 8 |  |  |  |  | 8
large knob w/lever | medium | 12 |  |  |  |  | 12
layer knob | small | 7 |  |  |  |  | 7
glass dome | small | 7 |  |  |  |  | 7
side hole 1 | small | 15 |  |  |  |  | 15
side hole 2 | small | 12 |  |  |  |  | 12
body lens connection | large | 25 |  |  |  |  | 25
simple switch | small | 3 |  |  |  |  | 3
top piece main body | meduim | [5 empty] | 0
Front plate | medium | 15 |  |  |  |  | 15
snug support | small | 10 |  |  |  |  | 10
complex knob rectangle | small | 8 |  |  |  |  | 8
complex knob slant cube | small | 7 |  |  |  |  | 7
complex knob mini knob | small | 13 |  |  |  |  | 13
complex knob body | small | 15 |  |  |  |  | 15
camera main body | large | [5 empty] | 0
front lever knob | small | [5 empty] | 0
front button | small | [5 empty] | 0
top latch | medium | [5 empty] | 0
| small | [5 empty] | 0
| small | [5 empty] | 0
| medium | [5 empty] | 0
| small | [5 empty] | 0
Note: all times are measured in minutes | [5 empty] | Total Medium-Res Model Time: | 187
High-Res Models
body frame | large | 10 | 20 |  |  |  | 30
watch face | medium | 15 | 6 |  |  |  | 21
watch glass | medium | 5 | 7 |  |  |  | 12
watch bracket BR | small | 8 | 5 |  |  |  | 13
watch bracket BL | small | 8 | 5 |  |  |  | 13
watch knob | small | 5 | 6 |  |  |  | 11
watch bracket TR | small | 8 | 5 |  |  |  | 13
watch bracket TL | small | 8 | 5 |  |  |  | 13
upper bracket holes | small | 8 | 7 |  |  |  | 15
10 sided bottom piece | medium | 2 | 3 |  |  |  | 5
bracket hole BR | small | 4 | 3 |  |  |  | 7
bracket hole BL | small | 4 | 3 |  |  |  | 7
hand stem | small | 2 | 2 |  |  |  | 4
hour hand | small | 10 | 15 |  |  |  | 25
minute hand | small | 8 | 10 |  |  |  | 18
second hand | small | 5 | 9 |  |  |  | 14
lower band bar | small | 4 | 4 |  |  |  | 8
lower band wrap | small | 7 | 7 |  |  |  | 14
band holes | large | 20 | 17 |  |  |  | 37
upper buckle part | small | 10 | 7 |  |  |  | 17
buckle bar | small | 7 | 4 |  |  |  | 11
buckle latch wrap | small | 10 | 7 |  |  |  | 17
buckle latch | small | 10 | 8 |  |  |  | 18
right buckle part | small | 9 | 9 |  |  |  | 18
left buckle part | small | 9 | 9 |  |  |  | 18
upper band bar | small | 5 | 3 |  |  |  | 8
upper bar wrap | small | 9 | 6 |  |  |  | 15
upper band strap | large | 15 | 7 |  |  |  | 22
right buckle wrap | small | 10 | 6 |  |  |  | 16
left buckle wrap | small | 10 | 6 |  |  |  | 16
Note: all times are measured in minutes | [5 empty] | Total High-Res Model Time: | 456
[6 empty] | Total Model Time: | 655

## Rigging and Animation
Model To Animate | Category | Rig Time | Animation Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Animation
Characters
BabaYagaHut | Large | 3 | 1 | 0.5 | 0.3 | 1 | 5.8
[6 empty] | Total Character Animation Time: | 5.8
[6 empty] | Total Rig & Animation Time: | 5.8

## Scripts
Scripts | Category | Coding Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Script
Player
PlayerMovement | Medium | 2 | 0.5 | 0.5 | 1 | 4
CameraControl | Small | 1 | 0.3 | 0.2 | 1 | 2.5
Jump | Small | 1 | 0.3 | 0.2 | 2 | 3.5
[5 empty] | Total Player Script Time: | 10
Game Events
GameReset | Small | 1 | 0.3 | 0.2 | 0.5 | 2
PlayerDeath | Small | 1 | 0.2 | 0.1 | 0.5 | 1.8
CollectItem | Medium | 2 | 0.5 | 0.5 | 1 | 4
[5 empty] | Total Events Script Time: | 7.8
Rendering
CullingObjects | Small | 1 | 0.2 | 0.2 | 1 | 2.4
TexReplacer(?) | Medium | 2 | 0.4 | 0.5 | 2 | 4.9
[5 empty] | Total Rendering Script Time: | 7.3
[5 empty] | Total Script Time: | 25.1

## VFX
VFX | Category | Art/Script Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For VFX
Camera
Shake | Medium | 0.3 | 1.5 | 0.3 | 1 | 3.1
Collect | Small | 0.3 | 1 | 0.2 | 1 | 2.5
Death | Medium | 0.3 | 1 | 0.3 | 1 | 2.6
[5 empty] | Total Camera VFX Time: | 8.2
Environmental
Fog | Large | 2 | 2 | 0.4 | 1 | 5.4
[5 empty] | Total Environmental VFX Time: | 5.4
Event
WoodCrack | Small | 1 | 1 | 0.5 | 0.5 | 3
DustPoof | Small | 1 | 1 | 0.5 | 0.5 | 3
CollectSparkle | Small | 1 | 1 | 0.3 | 0.5 | 2.8
[5 empty] | Total Event VFX Time: | 8.8
[5 empty] | Total VFX Time: | 22.4

## SFX
SFX | Category | Recording/Editing Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For SFX
Player
Damage | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Jump | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Landing | Small | 0.3 | 1 | 0.2 | 0.5 | 2
HeavyLanding | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Death | Medium | 1 | 1 | 0.2 | 1 | 3.2
[5 empty] | Total Player SFX Time: | 11.2
Environmental
BackgroundCreaks | Large | 2 | 1 | 0.5 | 1 | 4.5
BabaYagaHutStomp | Medium | 0.5 | 2 | 0.5 | 1 | 4
[5 empty] | Total Environmental SFX Time: | 8.5
Event
WoodCrack | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
DustPoof | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
CollectSparkle | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
[5 empty] | Total Event SFX Time: | 6.9
[5 empty] | Total SFX Time: | 26.6

## UI
UI | Category | Art/Scripting Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For UI
Camera
CrackScreen | Medium | 2 | 2 | 0.2 | 0.5 | 4.7
Collectable | Small | 1 | 1 | 0.2 | 0.5 | 2.7
FadeScreen | Small | 0.3 | 2 | 0.2 | 1 | 3.5
[5 empty] | Total Camera UI Time: | 10.9
Front End
TitleScreen | Large | 2 | 1 | 0.5 | 1 | 4.5
[5 empty] | Total Front End UI Time: | 4.5
Pause
PauseMenu | Large | 3 | 2 | 0.3 | 1 | 6.3
[5 empty] | Total Pause UI Time: | 6.3
[5 empty] | Total UI Time: | 21.7